## 24-01
No. | Card No. | Story Title | Module | Story Status Type | Assigned To | Target Process Status | Estimitaed Date | Actual Date | Comments
1 | 13643 | Add Branch > Dispute Document > Cannot select portion of the document | Subject Navigator | Bug | Shrinivas Sambhare | In Progress | 2020-02-05
2 | 13218 | Document Detail fields missing | Dispute Master | Bug | Anil Mori | Planned | 2020-01-31
3 | 11130 | Approve/Assign > Review Dispute Changes | Dispute Master | New | Anil Mori | Planned | 2020-02-07
4 | 8203 | Master List Field > Add new entry | All Masters | New | Anil Mori | Planned | 2020-02-13 |  | We need to look into this story that how we can perform this task
5 | 12576 | Upload Document > Treaty or Arbitration Rule > Unable to upload file with same name after deleting it | Dispute Document Master | Bug | Harsh Parikh, Shrinivas Sambhare, Jitesh Dhuruvala | Planned |  |  | Need to do R&D for how to forcefully stop the conversion in pdf to html algorithm
6 | 13478 | Upload Document > Can't convert file after it has been deleted | Dispute Document Master | Bug | Harsh Parikh, Shrinivas Sambhare, Jitesh Dhuruvala | Planned |  |  | Need to do R&D for how to forcefully stop the conversion in pdf to html algorithm
7 | 9644 | Analyze: Data Capture or Subject Navigator > Table of Contents | Subject Navigator | New | Shrinivas Sambhare | Planned | 2020-02-03
8 | 12684 | Document Flow > PDF version only | Dispute Document, Treaties & Arbitration | New | Harsh Parikh, Janak Thakkar | Planned | 2020-02-19
9 | 12763 | Dependent fields visible even if parent empty on master list record | All Masters | Bug | Anil Mori | In Progress | 2020-01-29
10 | 5922 | Analyze: Data Capture > Article Citator | Analyze/Tag | Bug | Shrinivas Sambhare | In Progress | 2020-01-31 |  | Text Overlap, Middle Text, Responsive html issue
11 | 5927 | Analyze: Data Capture > Jurisprudence Citator | Analyze/Tag | Bug | Shrinivas Sambhare | In Progress | 2020-01-31 |  | Text Overlap, Middle Text, Responsive html issue
12 | 9618 | Analyze > JP Citator > Modal > Paragraph(s) referenced | Analyze/Tag | Bug | Shrinivas Sambhare | In Progress | 2020-01-31 |  | Text Overlap, Middle Text, Responsive html issue
13 | 5928 | Analyze: Data Capture > Publication Citator | Analyze/Tag | Bug | Shrinivas Sambhare | In Progress | 2020-01-31 |  | Text Overlap, Middle Text, Responsive html issue
14 | 5930 | Analyze: Data Capture > Terms & Phrases | Analyze/Tag | Bug | Shrinivas Sambhare | In Progress | 2020-01-31 |  | Text Overlap, Middle Text, Responsive html issue
15 | 11129 | Analyze: Data Capture > Dispute Details | Dispute Master | New | Anil Mori | Planned | 2020-02-07
16 | 11207 | Add new meta-field > Dropdown/searchable dropdown > Use values from field | Meta Field | New | Harsh Parikh, Anil Mori | Planned |  |  | Need to take separte call with melisa for understanding requirements.
17 | 13108 | Treaties & Rules > Manually Create Provisions List | Treaties, Arbitartion Rule | New | Piyush Rathod | In Progress | 2020-01-31
18 | 12709 | Treaties & Rules > Multiple Languages > Upload | Treaties, Arbitartion Rule | New | Harsh Parikh, Janak Thakkar | In Progress | 2020-02-03
19 | 12715 | BITs/Treaties & Arbitration Rules > Groups | Treaties, Arbitartion Rule | New | Harsh Parikh, Janak Thakkar | In Progress | 2020-02-03
20 | 12716 | BITs /Treaties & Arbitration Rules > Groups > Mark as Primary | Treaties, Arbitartion Rule | New | Harsh Parikh, Janak Thakkar | In Progress | 2020-02-03
21 | 12717 | BITs/Treaties & Arbitration Rules > Groups > Remove from Group | Treaties, Arbitartion Rule | New | Harsh Parikh, Janak Thakkar | In Progress | 2020-02-03
22 | 12718 | BITs/Treaties & Arbitration Rules > Groups > Add to Group | Treaties, Arbitartion Rule | New | Harsh Parikh, Janak Thakkar | In Progress | 2020-02-03
23 | 12725 | Master Lists > BITs/Treaties & Rules > Search > Alternate Document Column | Treaties, Arbitartion Rule | New | Harsh Parikh, Janak Thakkar | In Progress | 2020-02-03
24 | 12869 | Master Lists > BITs/Treaties & Arbitration Rules > Alternate Documents Column | Treaties, Arbitartion Rule | New | Harsh Parikh, Janak Thakkar | In Progress | 2020-02-03
25 | 13648 | Treaties & Rules > Provisions list > Active provisions | Treaties, Arbitartion Rule | New | Piyush Rathod | In Progress | 2020-01-31
26 | 12640 | Dispute Document > Multiple languages > Upload | Dispute Document | New | Harsh Parikh, Janak Thakkar | Planned | 2020-02-14
27 | 12667 | Dispute Documents > Document Groups | Dispute Document | New | Harsh Parikh, Janak Thakkar | Planned | 2020-02-14
28 | 12687 | Dispute Documents > Document Groups > Mark as primary | Dispute Document | New | Harsh Parikh, Janak Thakkar | Planned | 2020-02-14
29 | 12869 | Dispute Documents > Document Groups > Remove from group | Dispute Document | New | Harsh Parikh, Janak Thakkar | Planned | 2020-02-14
30 | 12690 | Dispute Documents > Document Groups > Add to group | Dispute Document | New | Harsh Parikh, Janak Thakkar | Planned | 2020-02-14
31 | 9690 | Upload Document > Generate Table of Contents | Dispute Document | New | Shrinivas Sambhare | Planned | 2020-02-04
32 | 12059 | Upload document > Assess Conversion compatibility | Dispute Document, Treaties & Arbitration | New | Shrinivas Sambhare | Planned | 2020-02-19
33 | 12063 | Upload document > PDF version only | Dispute Document, Treaties & Arbitration | New | Shrinivas Sambhare | Planned | 2020-02-19
34 | 12552 | Masters Lists > Search by Name/UIN > Incorrect field type and behaviour | All Masters | Bug | Anil Mori | Planned | 2020-01-31
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50
51
52
53
54
55
56
57
58
59
60
61
62
63
64
65
66
67
68
69
70
71
72
73
74
75
76
77
78
79
80
81
82
83
84
85
86
87
88
89
90
91
92
93
94
95
96
97
98
99
100
101
102
103
104
105
106
107
108
109
110
111
112
113
114
115
116
117
118
119
120
121
122
123
124
125
126
127
128
129
130
131
132
133
134
135
136
137
138
139
140
141
142
143
144
145
146
147
148
149
150
151
152
153
154
155
156
157
158
159
160
161
162
163
164
165
166
167
168
169
170
171
172
173
174
175
176
177
178
179
180
181
182
183
184
185
186
187
188
189
190
191
192
193
194
195
196
197
198
199
200
201
202
203
204
205
206
207
208
209
210
211
212
213
214
215
216
217
218
219
220
221
222
223
224
225
226
227
228
229
230
231
232
233
234
235
236
237
238
239
240
241
242
243
244
245
246
247
248
249
250
251
252
253
254
255
256
257
258
259
260
261
262
263
264
265
266
267
268
269
270
271
272
273
274
275
276
277
278
279
280
281
282
283
284
285
286
287
288
289
290
291
292
293
294
295
296
297
298
299
300
301
302
303
304
305
306
307
308
309
310
311
312
313
314
315
316
317
318
319
320
321
322
323
324
325
326
327
328
329
330
331
332
333
334
335
336
337
338
339
340
341
342
343
344
345
346
347
348
349
350
351
352
353
354
355
356
357
358
359
360
361
362
363
364
365
366
367
368
369
370
371
372
373
374
375
376
377
378
379
380
381
382
383
384
385
386
387
388
389
390
391
392
393
394
395
396
397
398
399
400
401
402
403
404
405
406
407
408
409
410
411
412
413

## Value
Planned
In Progress
Blocked
In Testing
UAT