## Sheet1
Sr.No | Entity Type | # ID | Story Title | Module | Story Status Type | Assigned To | Target Process Status | Etimated Date | Actual Date | Comments
3 | UserStory | 8701 | Groups > Status | User Management |  |  | Blocked |  |  | Moving to blocked as highlighted criteria cannot be tested until subscriber side is developed
4 | UserStory | 8990 | Groups > Expiry Date | User Management |  |  | Blocked |  |  | Moving to blocked as highlighted criteria cannot be tested until subscriber side is developed
22 | UserStory | 8704 | Users > Status | User Management |  | Piyush Kanpariya | Blocked |  |  | Awaiting Approval (BLOCKED, NO TRIAL ACCOUNT FORM
54 | UserStory | 9724 | Tag Directory > Document References | Manage Tag Directory |  | Hiren Patel | In Testing | 2020-01-29
56 | UserStory | 9725 | Tag Directory > Document References > Tagged Excerpts | Manage Tag Directory |  |  | Blocked |  |  | Bug has been resolved (#13107 Tagged Excerpts > Not displaying in order) however setting this to blocked to make sure to re-test when the issue regarding multiple paragraph tagging has been resolved.
68 | UserStory | 9913 | Document Tagging > Browse Tagged Excerpts | Document Tagging |  | Hiren Patel | In Progress | 2020-02-04
71 | UserStory | 9922 | Document Tagging > Tag Directory | Document Tagging |  | Hiren Patel | In Testing | 2020-02-04
74 | UserStory | 9925 | Document Tagging > Add Tag to Excerpt | Document Tagging |  | Hiren Patel | In Testing | 2020-02-04
96 | UserStory | 10000 | Project/Document Fields | Manage Meta-Fields |  |  | Blocked |  |  | Waitin on #10005 Project/Document Fields > Reorder Fields
108 | UserStory | 10016 | Project/Document Fields > Add Field > Field Options > Show as front-end filter | Manage Meta-Fields |  |  | Blocked |  |  | Cannot be tested until front end is complete
114 | UserStory | 10005 | Project/Document Fields > Reorder Fields | Manage Meta-Fields |  | Hiren Patel | In Testing |  |  | Updated template pending from industrial side for over item functionality
122 | UserStory | 10103 | Field Sets > Add Field Set > Meta-Fields > Reorder Fields | Manage Meta-Fields |  | Hiren Patel | In Testing |  |  | Updated template pending from industrial side for over item functionality
193 | Bug | 12335 | Add Tag to Excerpt > Multiple highlights within single tag | Document Tagging | Document Tagging > Add Tag to Excerpt | Jitesh Dhuravala | Planned | 2020-02-04
209 | UserStory | 12540 | Field Sets and Parents/Dependent Fields | Manage Meta-Fields |  | Piyush Kanpariya | In Progress | 2020-01-28
217 | Bug | 13101 | Document References > Deleted file appears in tag directory |  | Tag Directory > Document References | Hiren Patel | In Testing | 2020-01-28
219 | Bug | 13346 | Document Tagging > Cannot select a tag within a tag | Document Tagging |  | Jitesh Dhuravala | Planned | 2020-02-04
220 | Bug | 13348 | Document Tagging > Tagging function intermittently broken | Document Tagging |  | Jitesh Dhuravala | Planned | 2020-02-05
221 | Bug | 13350 | Document Tagging > Delete tag modal not always displaying | Document Tagging |  | Jitesh Dhuravala | Planned | 2020-02-05
222 | Bug | 13353 | Document Tagging > Add tag never completes | Document Tagging |  | Hiren Patel | In Progress | 2020-02-04
223 | Bug | 13354 | Browse tagged excerpts > Not anchoring to correct location | Document Tagging | Document Tagging > Browse Tagged Excerpts | Hiren Patel | In Testing | 2020-02-06
224 | Bug | 13357 | Browse tagged excerpts > Not all tags are browsable | Document Tagging | Document Tagging > Browse Tagged Excerpts | Hiren Patel | In Testing | 2020-02-05
225 | Bug | 13358 | Document Tagging > Remove tag > highlight remains on bullet | Document Tagging |  | Jitesh Dhuravala | In Testing | 2020-02-08
230 | Bug | 13536 | Field Sets and Parents/Dependents > Removal of Test Set on Child | Manage Meta-Fields | Field Sets and Parents/Dependent Fields | Piyush Kanpariya | In Progress | 2020-01-28
232 | Bug | 13590 | Users > Status > Created Users | User Management | Users > Status | Piyush Kanpariya | Blocked | 2020-01-30