## Project Planning
ISLG Rebuild Development Plan
[6 empty] | Period Highlight: | 1 |  |  | Plan Duration | [5 empty] | Actual Start |  |  |  |  | % Complete |  |  |  |  | Actual (beyond plan) | [7 empty] | % Complete (beyond plan)
ACTIVITY | Phase | PLAN START | PLAN DURATION | ACTUAL START | ACTUAL DURATION | PERCENT COMPLETE | PERIODS
[7 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60 | 61 | 62 | 63 | 64 | 65 | 66 | 67 | 68 | 69 | 70 | 71 | 72 | 73 | 74 | 75 | 76 | 77 | 78 | 79 | 80 | 81 | 82 | 83 | 84 | 85 | 86 | 87 | 88 | 89 | 90 | 91 | 92 | 93 | 94 | 95 | 96 | 97 | 98 | 99 | 100 | 101 | 102 | 103 | 104 | 105 | 106 | 107 | 108 | 109 | 110 | 111 | 112 | 113 | 114 | 115 | 116 | 117 | 118 | 119 | 120 | 121 | 122 | 123 | 124 | 125 | 126 | 127 | 128 | 129 | 130 | 131 | 132 | 133 | 134 | 135 | 136 | 137 | 138 | 139 | 140 | 141 | 142 | 143 | 144 | 145 | 146 | 147 | 148 | 149 | 150 | 151 | 152 | 153 | 154 | 155 | 156 | 157 | 158 | 159 | 160 | 161 | 162 | 163 | 164 | 165 | 166 | 167 | 168 | 169 | 170 | 171 | 172 | 173 | 174 | 175 | 176 | 177 | 178 | 179 | 180
Database Designining | Phase 1 | 1 | 15 | 0 | 0 | 0%
Login | Phase 1 | 1 | 1 | 0 | 0 | 0%
Session Details | Phase 1 | 1 | 10 | 0 | 0 | 0%
Notepad Feature | Phase 2 | 3 | 12 | 0 | 0 | 0%
My Profile | Phase 2 | 14 | 2 | 0 | 0 | 0%
Login | Phase 1 | 1 | 1 | 0 | 0 | 0%
Master Tree | Phase 1 | 1 | 8 | 0 | 0 | 0%
Document database | Phase 1 | 1 | 30 | 0 | 0 | 0%
XML Agreement | Phase 1 | 16 | 3 | 0 | 0 | 0%
Admin FTS | Phase 1 | 2 | 5 | 0 | 0 | 0%
Web pages | Phase 1 | 11 | 6 | 0 | 0 | 0%
Settings | Phase 1 | 2 | 1 | 0 | 0 | 0%
Subscribers | Phase 1 | 9 | 5 | 0 | 0 | 0%
Admins | Phase 1 | 12 | 2 | 0 | 0 | 0%
Group management | Phase 1 | 20 | 3 | 0 | 0 | 0%
Reports | Phase 1 | 8 | 5 | 0 | 0 | 0%
Auto logout | Phase 1 | 18 | 1 | 0 | 0 | 0%
Phase 1 Delivery & User Acceptance |  | 31 | 5 | 0 | 0 | 0%
Subject Navigator Tree | Phase 2 | 37 | 36 | 0 | 0 | 0%
Subject Navigator Pages | Phase 2 | 37 | 35 | 0 | 0 | 0%
Tribunal Analysis | Phase 3 | 37 | 57 | 0 | 0 | 0%
Article Citator | Phase 2 | 37 | 10 | 0 | 0 | 0%
Jurisprudence Citator | Phase 2 | 37 | 28 | 0 | 0 | 0%
Publication Citator | Phase 2 | 37 | 19 | 0 | 0 | 0%
Phase 2 Delivery & User Acceptance |  | 73 | 5 | 0 | 0 | 0%
Term & Phrases | Phase 3 | 79 | 12 | 0 | 0 | 0%
Full Text Search | Phase 3 | 79 | 21 | 0 | 0 | 0%
Treaties & Rules | Phase 3 | 79 | 23 | 0 | 0 | 0%
Treaties & Rules - Agreement Page | Phase 3 | 79 | 10 | 0 | 0 | 0%
Dispute Documents | Phase 3 | 79 | 13 | 0 | 0 | 0%
Document Comparision | Phase 3 | 79 | 25 | 0 | 0 | 0%
Phase 3 Delivery & User Acceptance |  | 102 | 5 | 0 | 0 | 0%
Data Migration | Phase 4 | 107 | 20 | 0 | 0 | 0%
Data syncing between new and current site | Phase 4 | 107 | 25 | 0 | 0 | 0%
Search our collection | Phase 4 | 107 | 10 | 0 | 0 | 0%
Design Integration & CMS | Phase 4 | 107 | 10 | 0 | 0 | 0%
Dashboard | Phase 4 | 107 | 5 | 0 | 0 | 0%

## Development Estimation (hidden)
ISLG Rebuild Development Estimation
# | Milestone Name
Days
1 | Database Designining | 15
2 | Login | 1
3 | Session Details | 10
4 | Notepad Feature | 12
5 | My Profile | 2
6 | Auto logout | 1
8 | Subject Navigator Tree | 71
9 | Tribunal Analysis | 10
10 | Article Citator | 57
11 | Jurisprudence Citator | 28
12 | Publication Citator | 19
13 | Term & Phrases | 12
14 | Full Text Search | 21
15 | Treaties & Rules | 33
16 | Dispute Documents | 13
17 | Document Comparision | 25
18 | Data Migration | 20
19 | Data syncing between new and current site | 25
20 | Search our collection | 10
21 | Design Integration & CMS | 10
22 | Dashboard | 5
Total Man Days |  | 400
Total Man Months |  | 20