## Admin Feedbacks - 04012021
No. | Entity Type | ID | Name | Feature | Development Status | Status in TargetProcess | Development Completion Date | Comment | Morgan comments on priority
1 | UserStory | 13933 | Groups > Add new > Changes > Front end Permissions | Users | UAT | In Progress | 2021-01-04 | Depended on Story No. 8416 to chech UAT | Needs to be completed for before launch.
2 | UserStory | 8144 | Account Expiration | Users | UAT | In Progress | 2021-01-04 | Previous Status related change are not done, Auto Login is also not done same thing will discuss with Harsh Parikh | Needs to be completed for before launch.
3 | UserStory | 8416 | Groups > IP Access | Users | UAT | Planned | 2021-01-04 |  | Needs to be completed for before launch.
4 | UserStory | 20680 | IP Access > Disabled features | Users | Done | In Testing |  |  | Needs to be completed for before launch.
5 | UserStory | 20694 | IP Access > My Account | Users | Done | In Testing |  |  | Needs to be completed for before launch.
5 | UserStory | 9031 | Groups > Export Session Details | Users | UAT | In Testing | 2020-12-21 |  | Needs to be completed for before launch.
6 | UserStory | 20679 | Dashboard > IP Access | Users | Done | In Testing |  |  | Needs to be completed for before launch.
6 | UserStory | 9600 | SN Tree > Actions > Preview | Master Trees > Subject Navigator | UAT | In Testing | 2021-01-04 |  | Needs to be completed for before launch.
7 | Bug | 16878 | [ISLG Team Feedback] Sidebar Display to correspond to Excerpts | Analyzing/Tagging | UAT | In Progress | 2021-01-04 |  | Needs to be completed for before launch.
8 | Bug | 16883 | [ISLG Team Feedback] Reference sidebar lines should stagger | Analyzing/Tagging | Blocked | Backlog | 2021-01-04 | We tried our fully. We did so much R&D but technically it is not feasible to achieve while there was and Overlap Scenario. This scenario will happen in some cases. | Needs to ensure this isn't a show-stopper. See comments in TargetProcess.
9 | UserStory | 17867 | [ISLG Team Feedback] Automated Email Styling |  | UAT | In Testing | 2020-10-31 |  | Needs to be completed for before launch.
10 | Bug | 19950 | Analyze: Subject Navigator > Adding text to branch text created an additional bubble and sidebar | Analyzing/Tagging | UAT | UAT | 2020-12-21 |  | Needs to be completed for before launch.
11 | UserStory | 20166 | ISLG Team Feedback - Removing "pa" from display of paragraph number |  |  | Open |  | Not possible as need to change in whole application and Html Structure of all html as well | Schedule R&D in February
12 | Bug | 20325 | Analyze > Creating range references when a range exists doesn't create properly | Analyzing/Tagging | UAT | Backlog | 2021-01-31 |  | Needs to be completed for before launch.
13 | Bug | 20328 | Analyze > Creating overlapping excerpts doesn't show sidebar for newly added excerpt | Analyzing/Tagging | UAT | UAT | 2021-01-31 |  | Needs to be completed for before launch.
14 | Bug | 20582 | Analyze: Selecting text doesn't highlight all of the text | Analyzing/Tagging | UAT | Planned |  |  | Needs to be completed for before launch.
15 | UserStory | 20633 | Sub-Paragraph Changes > Sub-paragraphs to be included when referencing parent paragraph |  |  | Backlog |  | Fully R&D work. and might be not possible due to html structutre. need R&D | Schedule R&D in February
16 | UserStory | 20634 | Sub-Paragraph Changes > Can manually create paragraph range when there are sub paragraphs | Analyzing/Tagging |  | Backlog |  | Fully R&D work. and might be not possible due to html structutre. need R&D | Schedule R&D in February
17 | Bug | 20672 | SN Preview > Not able to view preview excerpt paragraphs | Master Trees > Subject Navigator | UAT | In Testing |  |  | Needs to be completed for before launch.
18 | Bug | 20675 | Groups > Export Session Details > Data likely not correct | Users | UAT | In Testing |  |  | Needs to be completed for before launch.
19 | Bug | 20703 | Account Expiration > Individual User who has expired account can still login | Users | UAT | Planned |  |  | Needs to be completed for before launch.
20 | Bug | 20707 | Automated Email Styling > Reset password button doesn't have enough contrast |  | UAT | In Testing |  |  | Needs to be completed for before launch.
21 | Bug | 20746 | Analyze > Deleting unassigned excerpts doesn't delete the selected one | Analyzing/Tagging | UAT | Planned |  |  | Needs to be completed for before launch.
22 | Bug | 20174 | ISLG Team Feedback - Uploading HTML doesn't display in 'Analyze' State |  | UAT | In Progress | 2021-01-31 |  | Needs to be completed for before launch.
23 | UserStory | 16905 | [ISLG Team Feedback] Additional fields in People and Organizations Master lists |  | UAT | In Progress | 2020-12-21 |  | Needs to be completed for before launch.
|  | 20678 | Beta/Existing App > Group setting doesn't affect individual setting | Users | UAT | In Testing |  |  | Needs to be completed for before launch.

## Manage Admin Reports - 04012021
No. | Entity Type | ID |  | Name | Feature | Development Status | Status in TargetProcess | Development Completion Date | Comment | Morgan comments on priority
1 | UserStory | 13049 | 13049 | Reports Table > Groups | Manage Reports | UAT | UAT | 2020-12-31 |  | Needs to be completed for before launch.
2 | UserStory | 13050 | 13050 | Reports Table > Reorder Reports | Manage Reports | UAT | UAT | 2020-12-31 |  | Needs to be completed for before launch.
3 | UserStory | 13051 | #N/A | Reports Table > Category Actions | Manage Reports | Done | In Progress | 2020-12-31 |  | Needs to be completed for before launch.
4 | UserStory | 13052 | #N/A | Reports Table > Type Actions | Manage Reports | Done | In Progress | 2020-12-31 |  | Needs to be completed for before launch.
5 | UserStory | 13053 | 13053 | Reports Table > Group Actions | Manage Reports | UAT | UAT | 2020-12-31 |  | Needs to be completed for before launch.
6 | UserStory | 20668 | #N/A | [Split] Reports Table > Report Actions | Manage Reports | Done | Planned |  |  | Needs to be completed for before launch.
7 | UserStory | 13055 | #N/A | Reports Table > Search | Manage Reports |  | In Progress | 2020-12-31 |  | Needs to be completed for before launch.
8 | UserStory | 13057 | 13057 | Add Report | Manage Reports | UAT | UAT | 2020-12-21 |  | Needs to be completed for before launch.
9 | UserStory | 13058 | 13058 | Add Report > Details | Manage Reports | UAT | UAT | 2020-12-31 |  | Needs to be completed for before launch.
10 | UserStory | 13062 | 13062 | Add Report > Dimensions & Filters > Rows (Individual Report) | Manage Reports | UAT | UAT | 2020-12-21 | Story is in block mode as we need to discuss with industrial team | Needs to be completed for before launch.
11 | UserStory | 13063 | 13063 | Report > Dimensions & Filters > Columns | Manage Reports | UAT | UAT | 2020-12-21 |  | Needs to be completed for before launch.
12 | UserStory | 13145 | 13145 | Report > Dimensions & Filters > Columns > Default column | Manage Reports | UAT | UAT | 2020-12-21 |  | Needs to be completed for before launch.
13 | UserStory | 13067 | #N/A | Report > Dimensions & Filters > Columns > Add/Edit Columns > Select Columns (Primary Category) | Manage Reports | In Progress | In Progress | 2020-12-21 | Depends on Quick view | Needs to be completed for before launch.
14 | UserStory | 13069 | 13069 | Report > Dimensions & Filters > Columns > Add/Edit Columns > Select Columns (Other Categories) | Manage Reports | UAT | UAT | 2020-12-21 |  | Needs to be completed for before launch.
15 | UserStory | 13082 | 13082 | Report > Dimensions & Filters > Columns > Add/Edit Columns > Create Custom Column | Manage Reports | UAT | UAT | 2020-12-21 |  | Needs to be completed for before launch.
16 | UserStory | 13068 | #N/A | Report >Â Dimensions & Filters > Columns > Add/Edit Columns > Column Options | Manage Reports |  | Backlog | 2020-12-21 |  | Needs to be completed for before launch.
17 | UserStory | 13197 | #N/A | Report > Dimensions & Filters > Columns > Actions > Edit Column | Manage Reports |  | In Progress | 2020-12-21 |  | Needs to be completed for before launch.
18 | UserStory | 13064 | #N/A | Report > Dimensions & Filters > Filter Data | Manage Reports | In Progress | Backlog | 2021-01-04 | chances to be completed on or before 06-01-2021 | Needs to be completed for before launch.
19 | UserStory | 13090 | #N/A | Report > Dimensions & Filters > Filter Data > Edit Filters and Rules (Default and Master List Record Columns) | Manage Reports | In Progress | Backlog | 2021-01-04 | chances to be completed on or before 06-01-2021 | Needs to be completed for before launch.
20 | UserStory | 13202 | #N/A | Report > Dimensions & Filters > Filter Data > Edit Filters and Rules (Field Columns) | Manage Reports |  | Backlog | 2021-01-04 | chances to be completed on or before 06-01-2021 | Needs to be completed for before launch.
21 | UserStory | 20683 | #N/A | Report > Dimensions & Filters > Filter Data > Edit Filters and Rules (Custom Columns) | Manage Reports |  | Planned |  | chances to be completed on or before 06-01-2021 | Needs to be completed for before launch.
22 | UserStory | 13091 | #N/A | Report > Dimensions & Filters > Filter Data > Prevent Front-End Override | Manage Reports |  | Backlog | 2021-01-04 | chances to be completed on or before 06-01-2021 | Needs to be completed for before launch.
23 | UserStory | 13065 | #N/A | Report > Quick View | Manage Reports |  | Planned | 2021-01-04 | will be released by 11-01-2021 as already discussed with Morgan | Needs to be completed for before launch.
24 | UserStory | 13060 | #N/A | Report > Linking | Manage Reports |  | Backlog | 2021-01-04 | will be released by 11-01-2021 as already discussed with Morgan | Needs to be completed for before launch.
25 | UserStory | 13061 | 13061 | Report > History | Manage Reports | UAT | UAT | 2020-12-21 |  | Needs to be completed for before launch.
26 | UserStory | 13119 | #N/A | Report > Preview | Manage Reports |  | Backlog | 2021-01-04 | will be released by 11-01-2021 as already discussed with Morgan | Needs to be completed for before launch.
27 | UserStory | 13207 | 13207 | Report > Saving and Publishing | Manage Reports | UAT | UAT | 2020-12-21 | Story is in block mode as we need to discuss with industrial team | Needs to be completed for before launch.
28 | UserStory | 13295 | #N/A | Report > Preview > Download Report | Manage Reports |  | Backlog | 2021-01-04 | will be released by 11-01-2021 as already discussed with Morgan | Needs to be completed for before launch.
29 | UserStory | 18549 | #N/A | Report > Individual Reports > Sequence | Manage Reports |  | Backlog | 2020-12-21 |  | Needs to be completed for before launch.
30 | UserStory | 18553 | #N/A | Reports > Comparative Reports > Sequence | Manage Reports |  | Backlog | 2020-12-21 |  | Needs to be completed for before launch.
31 | Bug | 20664 | 20664 | Report Category > Actions Menu > Add Report labels | Manage Reports | UAT | UAT |  |  | Needs to be completed for before launch.
32 | Bug | 20665 | 20665 | Report Type > Actions menu > labels incorrect | Manage Reports | UAT | UAT |  |  | Needs to be completed for before launch.
33 | Bug | 20666 | 20666 | Report > Action Menu > label incorrect | Manage Reports | UAT | UAT |  |  | Needs to be completed for before launch.
34 | Bug | 20667 | 20667 | Report Group > Actions Menu > labels incorrect | Manage Reports | UAT | UAT |  |  | Needs to be completed for before launch.
35 | Bug | 20670 | 20670 | Add Group > branch location | Manage Reports | UAT | UAT |  | UAT - Comment added in Target Process as development done as per discussion with Industrial Team | Needs to be completed for before launch.
36 | Bug | 20676 | 20676 | Reorder > page reload is jumpy | Manage Reports | UAT | UAT |  | Loader is already implement but still jumpy issue is there need to check in depth | Needs to be completed for before launch.
37 | Bug | 20677 | 20677 | reorder > reload > accordions collapsed | Manage Reports | UAT | UAT |  | technical challenge and seems not feasible. | Needs to be completed for before launch.
38 | Bug | 20684 | 20684 | Rows (Individual Report) > Typo in description text | Manage Reports | UAT | UAT |  |  | Needs to be completed for before launch.
39 | Bug | 20685 | 20685 | Rows (Individual Report) > Add row reference dialogue mixes up the report type and row type in description | Manage Reports | UAT | UAT |  |  | Needs to be completed for before launch.
40 | Bug | 20687 | 20687 | Rows (Individual Report) > Add row reference dialogue doesn't appear until user clicks on the page | Manage Reports | UAT | UAT |  | we have checked and it is working fine at our end on rebuild.demo . Please clear your cache and check again.please see attach video. | Needs to be completed for before launch.
41 | Bug | 20690 | 20690 | Rows (Individual Report) > Not all fields available to add as row reference fields | Manage Reports | UAT | UAT |  | Those fields which are associated with people master will be available in drop-down for selection as e.g: Claimant(s), Counsel (Claimant) are not associated with people master. | Needs to be completed for before launch.
42 | Bug | 20691 | 20691 | Default Column > Default column doesn't have actions menu | Manage Reports | UAT | UAT |  | UAT - Comment added in Target Process as development done as per discussion with Industrial Team | Needs to be completed for before launch.
43 | Bug | 20692 | 20692 | Primary Category > "Number of Values" & "Values" should appear after a hyphen | Manage Reports | UAT | UAT |  |  | Needs to be completed for before launch.
44 | Bug | 20693 | 20693 | Primary Category > Adding a column doesn't show the quick view | Manage Reports | UAT | UAT |  | Quick View development is pending yet. | Needs to be completed for before launch.
45 | Bug | 20696 | 20696 | Other Categories > Set Reference field dialogue text is reversed | Manage Reports | UAT | UAT |  |  | Needs to be completed for before launch.
46 | Bug | 20697 | 20697 | Custom Column > Creating a 2nd custom column shows previous columns heading | Manage Reports | UAT | UAT |  |  | Needs to be completed for before launch.
47 | Bug | 20698 | 20698 | Other Categories > Edit reference link doesn't always appear | Manage Reports | UAT | Planned |  | Depends on Report Filter module | Needs to be completed for before launch.
48 | Bug | 20704 | #N/A | Report search > parent branches do not show children | Manage Reports |  | Planned |  | Depends on Report Filter module | Needs to be completed for before launch.
49 | Bug | 20709 | 20709 | Individual Report > Edit Report Details | Manage Reports | UAT | UAT |  | UAT - Comment added in Target Process as development done as per discussion with Industrial Team | Needs to be completed for before launch.
50 | Bug | 20710 | 20710 | Delete report modal > not in view | Manage Reports | UAT | UAT |  | It is low priority task we can do this kind of change after post launch so please done this bug as of now. | Needs to be completed for before launch.
51 | Bug | 20711 | 20711 | Comparative report > edit report details | Manage Reports | UAT | UAT |  | UAT - Comment added in Target Process as development done as per discussion with Industrial Team | Needs to be completed for before launch.
52 | Bug | 20712 | 20712 | Duplicate rows in report | Manage Reports | UAT | UAT |  |  | Needs to be completed for before launch.
53 | Bug | 20713 | #N/A | Edit Column > Editing reference field doesn't show accurate information | Manage Reports |  | Planned |  | Depends on Report Filter module | Needs to be completed for before launch.
54 | Bug | 20714 | 20714 | Saving & Publishing > Error message should show quickly when user tries to publish a report without entering req info | Manage Reports | UAT | UAT |  |  | Needs to be completed for before launch.
55 | Bug | 20715 | 20715 | Saving & Publishing > While report is in draft mode and not yet published the toggle should be inactive | Manage Reports | UAT | UAT |  |  | Needs to be completed for before launch.
56 | Bug | 20716 | #N/A | Saving & Publishing > Create draft/edit draft of published document flow not implemented | Manage Reports | Blocked | Backlog |  | Need to discuss in this story regarding flow with Mel once they will be back from Holiday by 4th Jan 2021 | Needs to be completed for before launch.
57 | Bug | 20717 | #N/A | History > Not capturing publish document state | Manage Reports | Done | In Progress |  |  | Needs to be completed for before launch.
58 | Bug | 20718 | #N/A | History > Default order isn't reverse chronological order | Manage Reports | Done | In Progress |  |  | Needs to be completed for before launch.
59 | Bug | 20722 | #N/A | Rows (Individual Report) > Not able to create individual dispute report | Manage Reports | Blocked | Planned |  | Need to discuss in this story regarding flow with Mel once they will be back from Holiday by 4th Jan 2021 | Needs to be completed for before launch.
|  | 20716 | #N/A | Saving & Publishing > Create draft/edit draft of published document flow not implemented | Manage Reports |  | Backlog |  |  | Needs to be completed for before launch.
|  | 20717 | #N/A | History > Not capturing publish document state | Manage Reports |  | In Progress |  |  | Needs to be completed for before launch.
|  | 20718 | #N/A | History > Default order isn't reverse chronological order | Manage Reports |  | In Progress |  |  | Needs to be completed for before launch.
|  | 20722 | #N/A | Rows (Individual Report) > Not able to create individual dispute report | Manage Reports |  | Planned |  |  | Needs to be completed for before launch.
|  | 20715 | 20715 | Saving & Publishing > While report is in draft mode and not yet published the toggle should be inactive | Manage Reports | UAT | UAT |  |  | Needs to be completed for before launch.

## Subscribers
No. | Entity Type | ID | Name | Feature | Estimatted Completion Date | Status in TargetProcess | Development Completion Date | Comment | Morgan comments on priority | Features Suppressed
1 | UserStory | 7609 | Doc View > Keyword Search | Document View | 2021-01-11 | In Progress | 2020-11-30 |  | Needs to be completed for before launch.
2 | UserStory | 20596 | [Awaiting Development] RN > Entry > FTS > Full Document | Research Notepad | 2021-01-11 | Pending other Feature |  |  | Needs to be completed for before launch.
3 | UserStory | 11860 | RN > Entry > FTS > Excerpt | Research Notepad | 2021-01-11 | In Progress | 2020-11-30 |  | Needs to be completed for before launch.
4 | UserStory | 20600 | [Awaiting Development] RN > Entry > FTS Search | Research Notepad | 2021-01-11 | Pending other Feature |  |  | Needs to be completed for before launch.
5 | UserStory | 12152 | RN > Topic View > Download > FTS Document (Pinpoint Reference) | Research Notepad | 2021-01-11 | In Progress | 2020-11-30 |  | Needs to be completed for before launch.
6 | UserStory | 12150 | RN > Topic View > Download > FTS Dispute Document (Full) | Research Notepad | 2021-01-11 | In Progress | 2020-11-30 |  | Needs to be completed for before launch.
7 | UserStory | 7686 | FTS > Search | Full Text Search | 2021-01-11 | In Progress | 2020-11-30 |  | Needs to be completed for before launch.
8 | UserStory | 7688 | FTS > Search Results | Full Text Search | 2021-01-11 | In Progress | 2020-11-30 |  | Needs to be completed for before launch.
9 | UserStory | 7689 | FTS > Search Results > Sort | Full Text Search | 2021-01-11 | In Progress | 2020-11-30 |  | Needs to be completed for before launch.
10 | UserStory | 7691 | FTS > Search Results > Refine | Full Text Search | 2021-01-11 | In Progress | 2020-11-30 |  | Needs to be completed for before launch.
11 | UserStory | 7693 | FTS > Search Results > Card View > Preview Excerpt | Full Text Search | 2021-01-11 | In Progress | 2020-11-30 |  | Needs to be completed for before launch.
12 | UserStory | 19798 | [Awaiting Development] Custom Feed > Notifications | Dashboard |  | Pending other Feature | 2020-12-31 | Blocked due to Industrial Side and not clear for requirement | Needs to be completed for before launch. | Yes
13 | UserStory | 10042 | News Updates | Dashboard |  | Backlog | 2020-10-31 | Blocked due to Industrial Side and not clear for requirement | Needs to be completed for before launch. | Yes
14 | UserStory | 10045 | Feed > Upcoming Events | Dashboard |  | Backlog | 2020-10-31 | Blocked due to Industrial Side and not clear for requirement | Needs to be completed for before launch. | Yes
23 | UserStory | 12647 | Dashboard > Getting started with ISLG | Dashboard |  | Blocked | 2020-10-31 | Blocked due to Industrial Side and requirement is not clear | Needs to be completed for before launch. | Yes
24 | UserStory | 20177 | [Awaiting Development] Dashboard > First Login | Dashboard |  | Backlog |  | Blocked due to Industrial Side and requirement is not clear | Needs to be completed for before launch. | Yes
130 | Bug | 20605 | FTS > Doc view breadcrumb > does not link to search results | Document View |  | Planned |  | Technically not feasible as there is no functionality to save filtered data from FTS module. | Post-launch high priority release. | Yes
18 | UserStory | 11707 | Dispute Details > All > Displaying Legal Analytics Data | Disputes & Dispute Documents | 2021-01-11 | In Progress | 2020-09-30 |  | Needs to be completed for before launch.
19 | UserStory | 11977 | Doc View > Keyword Search > Via FTS | Document View | 2021-01-11 | In Progress | 2020-11-30 |  | Needs to be completed for before launch.
20 | UserStory | 17637 | [Awaiting Development] RN > Topic View > Bookmarks | Research Notepad | 2021-01-11 | In Progress | 2020-11-30 |  | Needs to be completed for before launch.
21 | UserStory | 12591 | FTS > Search Results > Document Reference Card | Full Text Search | 2021-01-11 | In Progress | 2020-11-30 |  | Needs to be completed for before launch.
22 | UserStory | 12595 | FTS > Search Results > Treaties & Rules Card | Full Text Search | 2021-01-11 | In Progress | 2020-11-30 |  | Needs to be completed for before launch.
38 | UserStory | 13764 | FTS > Search Results > Advanced Filters | Full Text Search |  | In Progress | 2020-11-30 | This will take 2-3 weeks of development time + Contegra team discussion + UAT time | Needs to be completed for before launch. | Yes
39 | UserStory | 13768 | FTS > Advanced Filter > Set/Add Additional Rule | Full Text Search |  | Blocked | 2020-11-30 |  | Needs to be completed for before launch. | Yes
40 | UserStory | 13771 | FTS > Advanced Filter > Edit Search Filter Rules | Full Text Search |  | In Progress | 2020-11-30 |  | Needs to be completed for before launch. | Yes
41 | UserStory | 13773 | FTS > Advanced Filter > Clear Individual Search Filter Rule | Full Text Search |  | Blocked | 2020-11-30 |  | Needs to be completed for before launch. | Yes
42 | UserStory | 13776 | FTS > Advanced Filter > Relation Between Rules (Logical Operators) | Full Text Search |  | Blocked | 2020-11-30 |  | Needs to be completed for before launch. | Yes
107 | Bug | 20563 | Advanced filter > Searchable dropdown > missing operator | Full Text Search |  | Planned |  | This will take 2-3 weeks of development time + Contegra team discussion + UAT time | Needs to be completed for before launch. | Yes
108 | Bug | 20564 | Advanced Filters > Legal Analytics > Jurisdiction > missing fields | Full Text Search |  | Planned |  |  | Needs to be completed for before launch. | Yes
109 | Bug | 20565 | Advanced Filters > Damaged & Interest > Missing filters | Full Text Search |  | In Progress |  |  | Needs to be completed for before launch. | Yes
31 | UserStory | 13720 | RN > Topic View > Download > FTS Search Results | Research Notepad | 2021-01-11 | In Progress | 2020-11-30 |  | Needs to be completed for before launch.
32 | UserStory | 13728 | RN > Entry > FTS > Treaty (Full) | Research Notepad | 2021-01-11 | In Progress | 2020-11-30 |  | Needs to be completed for before launch.
33 | UserStory | 13729 | RN > Entry > FTS > Treaty (Extract) | Research Notepad | 2021-01-11 | In Progress | 2020-11-30 |  | Needs to be completed for before launch.
34 | UserStory | 13730 | RN > Entry > FTS > Arbitration Rule (Full) | Research Notepad | 2021-01-11 | In Progress | 2020-11-30 |  | Needs to be completed for before launch.
35 | UserStory | 13731 | RN > Entry > FTS > Arbitration Rule (Extract) | Research Notepad | 2021-01-11 | In Progress | 2020-11-30 |  | Needs to be completed for before launch.
36 | UserStory | 13732 | RN > Topic View > Download > FTS > Treaty/Rule (Full) | Research Notepad | 2021-01-11 | In Progress | 2020-11-30 |  | Needs to be completed for before launch.
37 | UserStory | 13733 | RN > Topic View > Download > FTS > Treaty (Excerpt) | Research Notepad | 2021-01-11 | In Progress | 2020-11-30 |  | Needs to be completed for before launch.
110 | Bug | 20566 | Advanced filter > Costs > Missing all currency and percentage fields | Full Text Search |  | In Progress |  |  | Needs to be completed for before launch. | Yes
111 | Bug | 20567 | Advanced Search > Calendar selection > missing operators | Full Text Search |  | Planned |  |  | Needs to be completed for before launch. | Yes
112 | Bug | 20568 | Advanced filters > Unable to test all field types | Full Text Search |  | Backlog |  |  | Needs to be completed for before launch. | Yes
113 | Bug | 20569 | Advanced Filters > Treaties > Calendar selection > Missing operator options | Full Text Search |  | Planned |  |  | Needs to be completed for before launch. | Yes
15 | UserStory | 10046 | Perform Search | Global Search/Finder |  | Backlog | 2020-12-31 | This will take 3 weeks of development time + Contegra team discussion + UAT time | Needs to be completed for before launch. | Yes
43 | UserStory | 13806 | Reports | Reports/Legal Analytics | 2021-01-11 | Blocked | 2020-12-31 |  | Needs to be completed for before launch.
44 | UserStory | 13812 | Comparative Report Landing Pages > Follow Report Category | Reports/Legal Analytics | 2021-01-11 | In Progress | 2020-12-31 | Pending only notification link which are in other module linkage. we have covered in legal Report module and which are not affected in legal report. | Needs to be completed for before launch.
45 | UserStory | 13958 | Individual Record List Pages | Reports/Legal Analytics | 2021-01-04 | UAT | 2020-12-31 | Awaiting for client input.(User Story No: 20721,20724) | Needs to be completed for before launch.
46 | UserStory | 14006 | Individual Record List Pages > Follow Report Category | Reports/Legal Analytics | 2021-01-11 | In Progress | 2020-12-31 | Pending only notification link which are in other module linkage. we have covered in legal Report module and which are not affected in legal report. | Needs to be completed for before launch.
47 | UserStory | 13813 | Individual Record Landing Pages | Reports/Legal Analytics | 2021-01-04 | UAT | 2020-12-31 | Awaiting for client input.(User Story No: 20735) | Needs to be completed for before launch.
48 | UserStory | 13819 | Individual Record Landing/Report Pages > Change Record | Reports/Legal Analytics | 2021-01-04 | UAT | 2020-12-31 | UAT round 1 complete - blocked by #20722 Rows (Individual Report) > Not able to create individual dispute report, #20728 Ind Record Landing Page > Change modal needs different language- back to in progress | Needs to be completed for before launch.
49 | UserStory | 13814 | Individual Record Landing Pages > Follow Record | Reports/Legal Analytics | 2021-01-11 | In Progress | 2020-12-31 | UAT round 1 complete - blocked by #20722 Rows (Individual Report) > Not able to create individual dispute report- back to in progress | Needs to be completed for before launch.
50 | UserStory | 13815 | Individual Record Landing/Report Pages > Dispute Details | Reports/Legal Analytics | 2021-01-11 | In Progress | 2020-12-31 | Blocked by #20722 Rows (Individual Report) > Not able to create individual dispute report- back to in progress | Needs to be completed for before launch.
51 | UserStory | 13816 | Individual Record Landing/Report Pages > Person Details | Reports/Legal Analytics | 2021-01-04 | UAT | 2020-12-31 | Depend on 20736 | Needs to be completed for before launch.
52 | UserStory | 13817 | Individual Record Landing/Report Pages > Organization Details | Reports/Legal Analytics | 2021-01-04 | UAT | 2020-12-31 | UAT round 1 complete - Blocked by #20732 Ind Record Landing Page > Org/country page says expand person details, #20736 Person Details > URL not shown, #20737 Country Details > Flag upload field/special search tem is showing- back to in progress | Needs to be completed for before launch.
53 | UserStory | 13818 | Individual Record Landing/Report Pages > Country details | Reports/Legal Analytics | 2021-01-04 | UAT | 2020-12-31 | Depend on 20737 | Needs to be completed for before launch.
54 | UserStory | 13820 | Single Report > Comparative Report | Reports/Legal Analytics | 2021-01-11 | In Progress | 2020-12-31 | Depend on filters and table | Needs to be completed for before launch.
55 | UserStory | 20727 | [Split] Single Report > Comparative Report | Reports/Legal Analytics | 2021-01-11 | Planned |  | Depend on filters and table | Needs to be completed for before launch.
56 | UserStory | 13821 | Single Report > Individual Report | Reports/Legal Analytics | 2021-01-11 | In Progress | 2020-12-31 | Depend on filters and table | Needs to be completed for before launch.
57 | UserStory | 13823 | Single Report > Download Report | Reports/Legal Analytics | 2021-01-11 | In Progress | 2020-12-31 | Depend on filter and and report table but bugs resolved on 29 Dec 2020 | Needs to be completed for before launch.
58 | UserStory | 20730 | [Split] Single Report > Download Report | Reports/Legal Analytics | 2021-01-11 | Planned |  |  | Needs to be completed for before launch.
59 | UserStory | 13825 | Single Report > Report Table | Reports/Legal Analytics | 2021-01-11 | Planned | 2020-12-31 |  | Needs to be completed for before launch.
60 | UserStory | 13830 | Single Report > Report Filters | Reports/Legal Analytics | 2021-01-11 | Backlog | 2020-12-31 |  | Needs to be completed for before launch. | Yes
61 | UserStory | 13831 | Single Report > Report Filters > Manage Filters | Reports/Legal Analytics | 2021-01-11 | Backlog | 2020-12-31 |  | Needs to be completed for before launch. | Yes
62 | UserStory | 13832 | Single Report > Report Filters > Clear Filters | Reports/Legal Analytics | 2021-01-11 | Backlog | 2020-12-31 |  | Needs to be completed for before launch. | Yes
63 | UserStory | 13833 | Single Report > Report Filters > Reset Original Filters | Reports/Legal Analytics | 2021-01-11 | Backlog | 2020-12-31 |  | Needs to be completed for before launch. | Yes
64 | UserStory | 14044 | Single Report > Report Filters > Manage Rules | Reports/Legal Analytics | 2021-01-11 | Backlog | 2020-12-31 |  | Needs to be completed for before launch. | Yes
65 | UserStory | 14048 | Single Report > Report Filters > Add Rules | Reports/Legal Analytics | 2021-01-11 | Backlog | 2020-12-31 |  | Needs to be completed for before launch. | Yes
66 | UserStory | 14049 | Single Report > Report Filters > Edit Rules | Reports/Legal Analytics | 2021-01-11 | Backlog | 2020-12-31 |  | Needs to be completed for before launch. | Yes
67 | UserStory | 13835 | Single Report > Report Filters > Clear rules | Reports/Legal Analytics | 2021-01-11 | Backlog | 2020-12-31 |  | Needs to be completed for before launch. | Yes
68 | UserStory | 13836 | Single Report > Report Filters > Reset Original Rules | Reports/Legal Analytics | 2021-01-11 | Backlog | 2020-12-31 |  | Needs to be completed for before launch. | Yes
69 | UserStory | 13837 | Single Report > Report Filters > View Restricted Filters' Rules | Reports/Legal Analytics | 2021-01-11 | Backlog | 2020-12-31 |  | Needs to be completed for before launch. | Yes
73 | UserStory | 17983 | Beta vs Production Versions > Post Login Page | Marketing Site |  | Backlog | 2021-01-11 | Planned for 29th Release but might be delayed to cover UAT bugs/feedbacks | Needs to be completed for before launch.
74 | UserStory | 17984 | Beta vs Production Versions > In app switching of Versions | Marketing Site |  | Backlog | 2021-01-11 | Planned for 29th Release but might be delayed to cover UAT bugs/feedbacks | Needs to be completed for before launch.
72 | UserStory | 14031 | RN > Entry > Report (Legal Analytics) | Research Notepad | 2021-01-04 | UAT | 2020-12-31 |  | Needs to be completed for before launch.
75 | UserStory | 17986 | Login from Promos in Marketing Site | Marketing Site |  | Backlog | 2021-01-11 | Planned for 29th Release but might be delayed to cover UAT bugs/feedbacks | Needs to be completed for before launch. | Yes
76 | UserStory | 18087 | Create Pages > Dispute Details Document View | Marketing Site |  | Backlog | 2021-01-11 | Planned for 29th Release but might be delayed to cover UAT bugs/feedbacks | Needs to be completed for before launch.
77 | UserStory | 18088 | Create Pages > Dispute Document View | Marketing Site |  | Backlog | 2021-01-11 | Planned for 29th Release but might be delayed to cover UAT bugs/feedbacks | Needs to be completed for before launch.
78 | UserStory | 18097 | Create Pages > Dispute Document View > Document Details | Marketing Site |  | Backlog | 2021-01-11 | Planned for 29th Release but might be delayed to cover UAT bugs/feedbacks | Needs to be completed for before launch.
79 | UserStory | 18089 | Create Pages > Treaties/Rules Document View | Marketing Site |  | Backlog | 2021-01-11 | Planned for 29th Release but might be delayed to cover UAT bugs/feedbacks | Needs to be completed for before launch. | Yes
80 | UserStory | 17236 | Treaty/Rule Document View > Treaty/Rules Details | Marketing Site |  | Not in TargetProcess | Not in TargetProcess | Planned for 29th Release but might be delayed to cover UAT bugs/feedbacks |  | Yes
81 | UserStory | 18090 | Create Pages > Dispute Document Library | Marketing Site |  | Backlog | 2021-01-11 | Planned for 29th Release but might be delayed to cover UAT bugs/feedbacks | Needs to be completed for before launch.
82 | UserStory | 18101 | Dispute Document Library > Show & Sort | Marketing Site |  | Backlog | 2021-01-11 | Planned for 29th Release but might be delayed to cover UAT bugs/feedbacks | Needs to be completed for before launch. | Yes
83 | UserStory | 17089 | Dispute and Dispute Document > Searching, filtering, Result View | Marketing Site |  | Not in TargetProcess | Not in TargetProcess | Planned for 29th Release but might be delayed to cover UAT bugs/feedbacks |  | Yes
84 | UserStory | 18091 | Create Pages > Treaties & Rules Library | Marketing Site |  | Backlog | 2021-01-11 | Planned for 29th Release but might be delayed to cover UAT bugs/feedbacks | Needs to be completed for before launch.
85 | UserStory | 17083 | Treaties and Rules > Searching, Filtering, Result View | Marketing Site |  | Not in TargetProcess | Not in TargetProcess | Planned for 29th Release but might be delayed to cover UAT bugs/feedbacks |  | Yes
86 | UserStory | 18092 | Create Pages > Profile/Organization Listing Page | Marketing Site |  | Backlog | 2021-01-11 | Planned for 29th Release but might be delayed to cover UAT bugs/feedbacks | Needs to be completed for before launch.
87 | UserStory | 18093 | Create Pages > Report Landing Page | Marketing Site |  | Backlog | 2021-01-11 | Planned for 29th Release but might be delayed to cover UAT bugs/feedbacks | Needs to be completed for before launch.
89 | UserStory | 18977 | Data Visualizations > People Report Listing Page | Marketing Site |  | Backlog | 2021-01-11 | Planned for 29th Release but might be delayed to cover UAT bugs/feedbacks | Needs to be completed for before launch. | Yes
90 | UserStory | 18978 | Data Visualization > Organization Report Listing Page | Marketing Site |  | Backlog | 2021-01-11 | Planned for 29th Release but might be delayed to cover UAT bugs/feedbacks | Needs to be completed for before launch. | Yes
88 | UserStory | 18365 | [IMPROVEMENT] FTS Button Styling and Label Changes | Full Text Search | 2021-01-11 | In Progress | 2020-11-30 |  | Needs to be completed for before launch.
91 | UserStory | 18980 | Data Visualization > Person Landing Page | Marketing Site |  | Backlog | 2021-01-11 | Planned for 29th Release but might be delayed to cover UAT bugs/feedbacks | Needs to be completed for before launch. | Yes
92 | UserStory | 18981 | Data Visualization > Organization Landing Page | Marketing Site |  | Backlog | 2021-01-11 | Planned for 29th Release but might be delayed to cover UAT bugs/feedbacks | Needs to be completed for before launch. | Yes
102 | UserStory | 19843 | Integrate Events to Dashboard | Marketing Site |  | Backlog | 2021-01-11 |  | Needs to be completed for before launch. | Yes
103 | UserStory | 19844 | Integrate News Updates to Dashboard | Marketing Site |  | Backlog | 2021-01-11 |  | Needs to be completed for before launch. | Yes
25 | UserStory | 12954 | Notification Entry > Legal Analytics > Organization Landing Page | Notifications |  | Backlog | 2021-01-31 | Planned for 29th Release but might be delayed to cover UAT bugs/feedbacks | Post-launch high priority release. | Yes
26 | UserStory | 12955 | Notification Entry > Legal Analytics > Person Landing Page | Notifications |  | Backlog | 2021-01-31 | Planned for 29th Release but might be delayed to cover UAT bugs/feedbacks | Post-launch high priority release. | Yes
27 | UserStory | 12956 | Notification Entry > Legal Analytics > Country Landing Page | Notifications |  | Backlog | 2021-01-31 | Planned for 29th Release but might be delayed to cover UAT bugs/feedbacks | Post-launch high priority release. | Yes
28 | UserStory | 12982 | Notification Entry > Link Result > Organization Landing Page | Notifications |  | Backlog | 2020-12-31 | Planned for 29th Release but might be delayed to cover UAT bugs/feedbacks | Needs to be completed for before launch. | Yes
29 | UserStory | 12983 | Notification Entry > Link Result > Person Landing Page | Notifications |  | Backlog | 2021-01-31 | Planned for 29th Release but might be delayed to cover UAT bugs/feedbacks | Post-launch high priority release. | Yes
30 | UserStory | 12985 | Notification Entry > Link Result > Country Landing Page | Notifications |  | Backlog | 2021-01-31 | Planned for 29th Release but might be delayed to cover UAT bugs/feedbacks | Post-launch high priority release. | Yes
70 | UserStory | 13852 | Notification Entry > Legal Analytics > Comparative Report Categories | Notifications |  | Backlog | 2021-01-31 | Planned for 29th Release but might be delayed to cover UAT bugs/feedbacks | Post-launch high priority release. | Yes
100 | Bug | 19630 | Legal Analytics > Nested Field Set doesn't show all fields within the banded row | Disputes & Dispute Documents | 2021-01-11 | In Progress |  |  | Needs to be completed for before launch.
101 | Bug | 19633 | Legal Analytics > Fields that are not field sets show in banded rows | Disputes & Dispute Documents | 2021-01-11 | In Progress |  |  | Needs to be completed for before launch.
71 | UserStory | 13996 | Notification Entry > Legal Analytics > Individual Report Categories | Notifications |  | Backlog | 2021-01-31 | Planned for 29th Release but might be delayed to cover UAT bugs/feedbacks | Post-launch high priority release. | Yes
16 | UserStory | 20142 | Follow Topic | Reports/Legal Analytics |  | Backlog | 2020-12-31 | Planned for 29th Release but might be delayed to cover UAT bugs/feedbacks | Needs to be completed for before launch. | Yes
93 | UserStory | 18985 | Data Visualizations > People Landing Page | Reports/Legal Analytics |  | Backlog | 2021-01-11 | Planned for 29th Release but might be delayed to cover UAT bugs/feedbacks | Needs to be completed for before launch. | Yes
94 | UserStory | 18986 | Data Visualization > Organization Landing Page | Reports/Legal Analytics |  | Backlog | 2021-01-11 | Planned for 29th Release but might be delayed to cover UAT bugs/feedbacks | Needs to be completed for before launch. | Yes
95 | UserStory | 18987 | Data Visualizations > Country Listing Page | Reports/Legal Analytics |  | Backlog | 2021-01-11 | Planned for 29th Release but might be delayed to cover UAT bugs/feedbacks | Needs to be completed for before launch. | Yes
96 | UserStory | 18988 | Data Visualizations > Organization Listing Page | Reports/Legal Analytics |  | Backlog | 2021-01-11 | Planned for 29th Release but might be delayed to cover UAT bugs/feedbacks | Needs to be completed for before launch. | Yes
97 | UserStory | 18989 | Data Visualizations > People Listing Page | Reports/Legal Analytics |  | Backlog | 2021-01-11 | Planned for 29th Release but might be delayed to cover UAT bugs/feedbacks | Needs to be completed for before launch. | Yes
98 | UserStory | 18990 | Data Visualizations > Dispute Listing Page | Reports/Legal Analytics |  | Backlog | 2021-01-11 | Planned for 29th Release but might be delayed to cover UAT bugs/feedbacks | Needs to be completed for before launch. | Yes
134 | UserStory | 20617 | Report Filter > Column | Reports/Legal Analytics |  | Backlog |  |  | Needs to be completed for before launch. | Yes
135 | UserStory | 20618 | Report Filter > Custom Column | Reports/Legal Analytics |  | Planned |  |  | Needs to be completed for before launch. | Yes
17 | UserStory | 10030 | SN > Tree > Search | Subject Navigator |  | Backlog | 2020-09-30 | Blocked by Contegra Side - already raised to Radomir by tomorrow and get update | Needs to be completed for before launch.
99 | Bug | 19515 | Any words search > no highlight | Subject Navigator |  | Backlog |  |  | Needs to be completed for before launch.
114 | Bug | 20570 | [IMPROVEMENT] Advanced Filters > Treaties > exclude placeholder and common URL source | Full Text Search | 2021-01-11 | Planned |  |  | Needs to be completed for before launch.
115 | Bug | 20572 | FTS > Cannot perform search with filters |  | 2021-01-11 | Planned |  |  | Needs to be completed for before launch.
116 | Bug | 20573 | Advanced filters > missing validation | Full Text Search | 2021-01-11 | In Progress |  |  | Needs to be completed for before launch. | Yes
117 | Bug | 20579 | Search results with no pinpoint references | Full Text Search | 2021-01-11 | Planned |  |  | Needs to be completed for before launch.
118 | Bug | 20585 | Search result > does not load document | Full Text Search | 2021-01-11 | Planned |  |  | Needs to be completed for before launch.
119 | Bug | 20586 | Search with basic filter does not work | Full Text Search | 2021-01-11 | Planned |  |  | Needs to be completed for before launch.
120 | Bug | 20587 | Cannot access document view | Document View | 2021-01-11 | Planned |  |  | Needs to be completed for before launch.
121 | Bug | 20588 | exiting document view | Document View | 2021-01-11 | Planned |  |  | Needs to be completed for before launch.
122 | Bug | 20592 | FTS Button Styling > 'Filter Results by' label still is the same | Full Text Search | 2021-01-11 | Planned |  |  | Needs to be completed for before launch.
123 | Bug | 20593 | FTS Button Styling > "Refine Filters" label to change to "Basic Filters | Full Text Search | 2021-01-11 | Planned |  |  | Needs to be completed for before launch.
124 | Bug | 20594 | FTS Button Styling > Remove Icon before the 'refine filters/basic filters' option | Full Text Search | 2021-01-11 | Planned |  |  | Needs to be completed for before launch.
125 | Bug | 20595 | FTS Button Styling > Advanced Filters Modal still says "Save filters" | Full Text Search | 2021-01-11 | Planned |  |  | Needs to be completed for before launch.
126 | Bug | 20599 | Basic Filter Modal > Linguistic Aids checkboxes not visible | Full Text Search | 2021-01-11 | Planned |  |  | Needs to be completed for before launch.
127 | Bug | 20601 | RN > Download > Clicking on the link from the excel doesn't lead me to the destination | Research Notepad | 2021-01-11 | Planned |  |  | Needs to be completed for before launch.
128 | Bug | 20602 | RN > Download > Filter applied label should reflect accurate label | Full Text Search | 2021-01-11 | Planned |  |  | Needs to be completed for before launch.
104 | UserStory | 20167 | ISLG Team Feedback - Removing "pa" from display of paragraph number |  |  | Backlog | 2021-01-31 | It requires a lot changes in whole application and html structure | Post-launch high priority release. | Yes
105 | UserStory | 20172 | ISLG Team feedback - Maintain Formatting when copying excerpt |  |  | Backlog | 2021-01-31 | Planned for 29th Release but might be delayed to cover UAT bugs/feedbacks | Post-launch high priority release. | Yes
131 | Bug | 20611 | Search > Not able to search without inputting a keyword | Full Text Search | 2021-01-11 | Planned |  |  | Needs to be completed for before launch.
132 | Bug | 20612 | Search > Boolean search not working | Full Text Search | 2021-01-11 | Planned |  |  | Needs to be completed for before launch.
133 | Bug | 20613 | Search > Fuzzy Typo not working | Full Text Search | 2021-01-11 | Planned |  |  | Needs to be completed for before launch.
106 | UserStory | 20173 | ISLG Team Feedback - Only full paragraphs to appear highlighted |  |  | Backlog | 2021-01-31 | Planned for 29th Release but might be delayed to cover UAT bugs/feedbacks | Post-launch high priority release. | Yes
129 | Bug | 20603 | FTS doc view > keyword appearances in list do not correspond to doc text |  |  | Planned |  |  | Needs to be completed for before launch.
136 | UserStory | 20679 | Dashboard > IP Access | Dashboard | 2021-01-04 | UAT |  |  | Needs to be completed for before launch.
137 | UserStory | 20680 | IP Access > Disabled features |  | 2021-01-04 | UAT |  |  | Needs to be completed for before launch.
138 | UserStory | 20694 | IP Access > My Account |  | 2021-01-04 | UAT |  |  | Needs to be completed for before launch.
139 | UserStory | 20720 | DD References > HTML unavailable for analysis |  |  | Backlog |  |  | Needs to be completed for before launch.
140 | Bug | 20721 | Individual Record List > People/organizations with images change the ratio of the image container | Reports/Legal Analytics | 2021-01-04 | UAT |  | There is no functionality for Auto Crop and need that revised template from Industrial | Needs to be completed for before launch.
141 | Bug | 20723 | Individual Record List > Follow should only be on the dispute page | Reports/Legal Analytics | 2021-01-04 | UAT |  |  | Needs to be completed for before launch. | Yes
142 | Bug | 20724 | Individual Record List > Comparative callout has wrong copy | Reports/Legal Analytics | 2021-01-11 | In Progress |  | We have developed the template you have provided and as per user story. There is nothing mention about the call out in user story. Wireframe Link :https://projects.invisionapp.com/share/J5QSGXWXM4R#/screens/403222833_LegalAnalytics_SCREEN_List_People User story : https://industrialagency.tpondemand.com/RestUI/Board.aspx#page=board/5596457270758793748&appConfig=eyJhY2lkIjoiNEIyRDU0NTZFNkFEOUY1MUQwQzA5QzI5QjBBNjM1OTMifQ==&boardPopup=userstory/13958/silent | Needs to be completed for before launch.
143 | Bug | 20725 | Ind Record Landing Page > & symbol in breadcrumb not working | Reports/Legal Analytics | 2021-01-04 | UAT |  |  | Needs to be completed for before launch.
144 | Bug | 20728 | Ind Record Landing Page > Change modal needs different language | Reports/Legal Analytics | 2021-01-04 | UAT |  |  | Needs to be completed for before launch.
145 | Bug | 20729 | Report Download > Individual Report > Incorrect Details |  | 2021-01-04 | UAT |  |  | Needs to be completed for before launch.
146 | Bug | 20731 | Individual Report Download > Person Record Details Incorrect | Reports/Legal Analytics | 2021-01-04 | UAT |  |  | Needs to be completed for before launch.
147 | Bug | 20732 | Ind Record Landing Page > Org/country page says expand person details | Reports/Legal Analytics | 2021-01-04 | UAT |  |  | Needs to be completed for before launch.
148 | Bug | 20733 | Ind Record Landing Page > People landing page shows reports that don't exist on admin side | Reports/Legal Analytics | 2021-01-04 | UAT |  |  | Needs to be completed for before launch.
149 | Bug | 20734 | Individual Report Download > Organization Record Detials missing | Reports/Legal Analytics | 2021-01-04 | UAT |  |  | Needs to be completed for before launch.
150 | Bug | 20735 | Ind Record Landing Page > Comparative report callout has wrong copy | Reports/Legal Analytics | 2021-01-11 | In Progress |  | We have developed the template you have provided and as per user story. There is nothing mention about the call out in user story. Wireframe Link : https://projects.invisionapp.com/share/J5QSGXWXM4R#/screens/402688397_LegalAnalytics_SCREEN_IndividualLanding User story : https://industrialagency.tpondemand.com/RestUI/Board.aspx#page=board/5596457270758793748&appConfig=eyJhY2lkIjoiNEIyRDU0NTZFNkFEOUY1MUQwQzA5QzI5QjBBNjM1OTMifQ==&boardPopup=userstory/13813/silent | Needs to be completed for before launch.
151 | Bug | 20736 | Person Details > URL not shown | Reports/Legal Analytics | 2021-01-04 | UAT |  |  | Needs to be completed for before launch.
152 | Bug | 20737 | Country Details > Flag upload field/special search tem is showing | Reports/Legal Analytics | 2021-01-04 | UAT |  |  | Needs to be completed for before launch.
153 | Bug | 20738 | Report > RN Legal Analytics label to change to ISLG Reports | Research Notepad | 2021-01-04 | UAT |  |  | Needs to be completed for before launch.
154 | Bug | 20740 | Reports > Card in the Research Notepad module shouldn't have a field for topic | Research Notepad | 2021-01-04 | UAT |  |  | Needs to be completed for before launch.